## Slide 1: Sprint 56 Show and Tell 6 November 2024
C Squad
Digital Team

## Slide 2
Sprint goal
Launch garden waste
campaign for 2025

## Slide 3: Send Garden Waste email to early adopters
Garden Waste
Email sent to 358 residents who signed up to be reminded about Garden Waste subscriptions for 2025.
Email sent on Friday 1 November as an 'early adopters' offer before Garden Waste opened up to everyone on Monday 4 November
67 online sign ups from this email over the weekend

## Slide 4: Garden Waste subscriptions reopened
Garden Waste
www.gateshead.gov.uk/gardenwaste
Signups reopened on the website and Customer Contact on Monday 4 November

## Slide 5: Send Garden Waste email to all past subscribers
Garden Waste
Email sent to 20,731 residents who have signed up to Garden Waste in the past
Email sent at 2pm on Tuesday 6 November to coincide with letters arriving that had been sent to all eligible households
As of 9am on 6 November, we had 1463 online sign ups (95%) and a total of 1484 altogether.

## Slide 6
Direct payments - user research analysis

## Slide 7: Context
Direct payments
Working on direct payments for a while to investigate the relatively poor uptake rate and build in improvements to the new Direct Payment Support Service
User research undertaken to find out more about the experience of those receiving direct payments and gather insights from this
9 interviews total
Focus group with Jewish Community Council of Gateshead hopefully pending
Have started analysis on interviews

## Slide 8: Analysis process so far
Direct payments
Transcription highlighting key quotes affinity mapping spreadsheet
Spreadsheet now contains our key quotes categorised into themes and sub-themes
Have included more colleagues in analysis to improve the quality and reduce risk of bias –highlighting key quotes and points

## Slide 9: Analysis next steps
Direct payments
Some more squad involvement with analysis
Draw out pain points and suggestions
Customer journey mapping to highlight the different experiences and needs of different users
Identifying user needs. Just as important as the user suggestions…

## Slide 10: Deployments

## Slide 11: Thank you
That's all folks!